## Slide 1
WORKING SESSION
Profound × Azalea
Tyler ADS Partnership
August 10, 2026 | 1:00–5:00 p.m. CT | Austin area
Objective: sign the framework, assign the launch work, and begin implementation.
Notes: [Sources]
- Profound Counsel Memorandum - Working Draft Revision 1.00 - 080626.
- Profound Financial Advisor Memorandum - Working Draft Revision 1.00 - 080626.
- Internal working assumptions confirmed by Geoff Schackmann, August 6–7, 2026.

## Slide 2
PROFOUND × AZALEA | TYLER ADS
Today should convert alignment into an executable path
02
01
Confirm the operating and economic framework
02
Resolve authority, staffing, payroll, EMR and vendor decisions
03
Agree on TULIP, PECOS and Medicare approval workstreams
04
Assign accountable owners and target dates
05
Approve the advisor packages and document architecture
06
Finalize the non-binding term sheet for signature
Notes: Use this as the upfront contract for the four-hour working session.
[Sources]
- Internal working assumptions confirmed by Geoff Schackmann, August 6, 2026.

## Slide 3
PROFOUND × AZALEA | TYLER ADS
The concept is aligned; documentation and launch controls remain
03
Aligned in principle
• Tyler ADS under Profound’s provider platform
• Azalea funds the Tyler operation
• $7,500 monthly implementation and oversight fee
• Direct costs reimbursed at cost, without markup
Still to document
• Profound authority and the launch go/no-go
• September payment instrument and Patrick’s transition election
• Payroll, EMR, billing, vendor and cash controls
• Advisor redlines and definitive-document path
Working status
Agreement in principle — subject to financial-advisor review, legal review, regulatory approval and definitive documents.
Notes: [Sources]
- Profound Counsel Memorandum - Working Draft Revision 1.00 - 080626.
- Profound Financial Advisor Memorandum - Working Draft Revision 1.00 - 080626.
- Internal working assumptions confirmed by Geoff Schackmann, August 6–7, 2026.

## Slide 4
PROFOUND × AZALEA | TYLER ADS
Profound receives near-term economics without funding the Tyler launch
04
Immediate value
$7,500 monthly fee
Full reimbursement of direct Tyler costs
No Tyler capital obligation
Transition consideration selected by Patrick
Azalea funding
$250,000 committed equity
Approximately $20,000 spent; approximately $230,000 available
No bank debt assumed for launch
Cap table: Geoff 36% | Jim 25% | employee group 39%
Strategic option
A 12-month bridge with a mutual extension option
A working relationship that may continue after Azalea’s standalone platform
No automatic long-term equity or permanent dependency
Notes: [Sources]
- Profound Counsel Memorandum - Working Draft Revision 1.00 - 080626.
- Profound Financial Advisor Memorandum - Working Draft Revision 1.00 - 080626.
- Internal working assumptions confirmed by Geoff Schackmann, August 6–7, 2026.

## Slide 5
PROFOUND × AZALEA | TYLER ADS
The entities are distinct; Profound remains the provider of record
05
Tyler Hospice Hold, LLC
100% owner of future Tyler operating company
Funds Tyler operations
Tyler operating company
Identified; diligence underway
Intended DBA: Azalea Hospice
Profound Hospice
Licensed provider
Final clinical and compliance authority
Payers
Claims and
receipts
Profound must remain the actual provider—not a billing conduit.
Tyler Hospice Hold, LLC is intended to own 100% of the future Tyler operating company. That company has been identified and is in diligence; “Azalea Hospice” is the intended DBA. Profound remains the provider of record.
Notes: [Sources]
- Profound Counsel Memorandum - Working Draft Revision 1.00 - 080626.
- Profound Financial Advisor Memorandum - Working Draft Revision 1.00 - 080626.
- Internal working assumptions confirmed by Geoff Schackmann, August 6–7, 2026.

## Slide 6
PROFOUND × AZALEA | TYLER ADS
The economics are fixed, transparent and independent of referrals
06
Monthly
$7,500
Target: September 1
Payment requires an expressly binding implementation provision or a short implementation letter after the framework is signed.
Direct costs
Approved Tyler costs at actual cost
No markup
Documented and reconciled monthly
No Profound capital obligation
Patrick’s election
Patrick elects before definitive documents
Option A | $25,000 transition cash
Option B | $50,000 convertible note; terms developed with counsel
No exclusivity
Notes: [Sources]
- Profound Counsel Memorandum - Working Draft Revision 1.00 - 080626.
- Profound Financial Advisor Memorandum - Working Draft Revision 1.00 - 080626.
- Internal working assumptions confirmed by Geoff Schackmann, August 6–7, 2026.

## Slide 7
PROFOUND × AZALEA | TYLER ADS
Profound’s protections are embedded in the operating model
07
01
Authority
Final admissions, clinical, policy, QAPI, billing and stop-admission control
02
Cash
Profound-controlled bank account and payer receipts
03
Visibility
Tyler claims, ERA, AR, payroll and vendor reporting
04
Funding
Azalea-prefunded payroll, operating costs and required reserves
05
Recourse
Insurance, indemnity, beneficiary choice, claims runout and wind-down obligations
Notes: [Sources]
- Profound Counsel Memorandum - Working Draft Revision 1.00 - 080626.
- Profound Financial Advisor Memorandum - Working Draft Revision 1.00 - 080626.
- Internal working assumptions confirmed by Geoff Schackmann, August 6–7, 2026.

## Slide 8
PROFOUND × AZALEA | TYLER ADS
The teams integrate around clear decision rights
08
Tyler / Azalea leads
• Local execution and census development
• Recruiting and staffing recommendations
• Scheduling and performance management
• Marketing and referral-development activity
• Tyler budget and operating reporting
• Technology and vendor recommendations
Profound retains final authority
• Patient acceptance and discharge
• Eligibility, certification and plan of care
• Clinical policies and QAPI
• Provider enrollment, claims and refunds
• Final clinical employment decisions
• Stop-admission and compliance intervention
Integration action
Introduce both teams, explain the shared model, and publish one escalation path before the first admission.
Notes: Silas should lead this section and invite Patrick to map his existing team into the roles.
[Sources]
- Texas HHSC ADS guidance on authority and supervision: https://apps.hhs.texas.gov/providers/hcssa/cbt/module6/HCSSA_PresurveyCBT_Module_6_0603202121.html

## Slide 9
PROFOUND × AZALEA | TYLER ADS
Vendor choices should reduce risk—not create friction
09
FireNote
Azalea’s proposed Tyler EMR
Rationale: documentation consistency, clinician productivity and compliance visibility
Decision requires Profound control, administrator access, record export, claims workflow and security review
Hospice Tools
Profound’s current EMR
Known operating environment for Profound
Published pricing starts at $85 per user/month; billing and clearinghouse services may be separate
Evaluate integration and total workflow cost
DME Express
Azalea’s current DME partner
Continuity reduces patient and caregiver disruption
Profound must approve a new agreement or valid assignment
Confirm formulary, service levels, integration, pricing and invoicing
Notes: Do not present FireNote as predetermined. Present a controlled clinical review and shared decision.
[Sources]
- FireNote product claims (vendor-provided): https://firenote.health/compliance-solutions and https://firenote.health/how-firenote-works
- Hospice Tools pricing and product claims (vendor-provided): https://www.hospicetools.com/pricing/
- DME Express integration claims (vendor-provided): https://dmeexpress.com/technology/

## Slide 10
PROFOUND × AZALEA | TYLER ADS
A clinical working session can decide the EMR based on evidence
10
Participants
Patrick • Patrick’s RN spouse • Profound clinical lead • Dana • Silas • FireNote implementation lead
1
Demonstrate
Admission, care plan, IDG, orders, HOPE, supervisory visits and ADR retrieval
2
Validate control
Profound administrator access, audit logs, policy alignment, record retention and export
3
Validate billing
NPI/CCN configuration, NOE and claim workflow, clearinghouse, ERA and AR reporting
4
Decide
Approve FireNote, retain Hospice Tools, or define a controlled alternative
Notes: Offer to schedule this follow-up immediately. The clinical users should decide against agreed acceptance criteria.
[Sources]
- 42 C.F.R. § 418.104: https://www.law.cornell.edu/cfr/text/42/418.104
- CMS-855A medical-record storage and provider-control instructions: https://www.cms.gov/medicare/cms-forms/cms-forms/downloads/cms855a.pdf

## Slide 11
PROFOUND × AZALEA | TYLER ADS
Core clinical staff should sit on Profound payroll; Azalea funds the cost
11
Recommended base case
• Profound is W-2 employer for core clinical staff
• Azalea prefunds wages, taxes and benefits
• Tyler is a separate location and cost center
• One authoritative payroll-tax filer
• Gusto only if Profound’s payroll advisor validates the configuration
• Azalea employs appropriate nonclinical staff
Why this is cleaner
• Aligns employment with the certified provider
• Preserves Profound’s supervision and policy authority
• Avoids routine contracting of core services
• Prevents duplicate quarterly payroll filings
• Produces location-level payroll reporting
• Keeps Azalea economically responsible
Decision needed
Authorize payroll and healthcare counsel to validate the employer, funding and filing mechanics immediately.
Notes: Do not promise that two unrelated payroll providers can file under one EIN. The base case requires one filer.
[Sources]
- 42 C.F.R. § 418.64 core-services employment rule: https://ecfr.io/Title-42/Section-418.64
- 42 C.F.R. § 418.100 governing-body and administrator requirements: https://www.ecfr.gov/current/title-42/chapter-IV/subchapter-B/part-418/subpart-D/section-418.100
- Gusto guidance on one filer per quarter: https://support.gusto.com/article/250327190420853/payroll-tax-responsibilities-when-switching-to-gusto

## Slide 12
PROFOUND × AZALEA | TYLER ADS
One bank account and one Tyler subledger keep cash controls clean
12
Payers
Deposit into Profound-controlled account
Tyler subledger
Patient, claim, ERA, AR and cash attribution
Payment waterfall
Care + payroll → reserves → direct costs → fee → advances → true-up
Report
Close within 10 business days
Minimum monthly reporting
• Claims submitted, paid, denied and pending
• ERA and cash receipts by patient and service month
• Payroll, pharmacy, DME and other direct costs
• Fee, reserve activity and working-capital balance
• Reconciliation, exceptions and agreed true-up
Control principle
Profound controls payer cash. Azalea receives complete visibility and contractual reconciliation rights.
Notes: [Sources]
- Profound Counsel Memorandum - Working Draft Revision 1.00 - 080626.
- Profound Financial Advisor Memorandum - Working Draft Revision 1.00 - 080626.
- Internal working assumptions confirmed by Geoff Schackmann, August 6–7, 2026.

## Slide 13
PROFOUND × AZALEA | TYLER ADS
Billing readiness is a regulatory project—not a credential handoff
13
Proposed Tyler ADS location: 13387 North Highway 69, Tyler, Texas
1
Confirm eligibility
Service area, location, license status, accreditation and MAC pathway
2
Texas TULIP
Secure HHSC ADS approval, parent-license link and service-area confirmation
3
PECOS / 855A
Add Tyler location; obtain MAC/CMS approval and the effective date
4
Approval + build
Close survey/AO, payer, staffing, EMR, claims, payroll, vendor and testing gates
5
First admission
Only after approvals are effective and Profound signs the readiness certificate
August 31 is an aggressive target. Submission is not approval; the ADS launches only after every required effective date and written go/no-go condition is satisfied.
Notes: Ask Patrick to identify his MAC, accreditation organization, current licensed service area and TULIP access during the meeting.
[Sources]
- Tyler ADS address provided by Geoff Schackmann on August 6, 2026.
- Texas TULIP training guide: https://www.hhs.texas.gov/sites/default/files/documents/doing-business-with-hhs/licensing-credentialing-regulation/tulip/tulip-training-guide.pdf
- Texas HHSC ADS guidance: https://apps.hhs.texas.gov/providers/hcssa/cbt/module6/HCSSA_PresurveyCBT_Module_6_0603202121.html
- 42 C.F.R. § 418.100(f): https://www.ecfr.gov/current/title-42/chapter-IV/subchapter-B/part-418/subpart-D/section-418.100
- CMS-855A, Section 4: https://www.cms.gov/medicare/cms-forms/cms-forms/downloads/cms855a.pdf

## Slide 14
PROFOUND × AZALEA | TYLER ADS
The RACI keeps Profound accountable without making Patrick do everything
14
Workstream
Patrick
Profound role
Geoff
Silas
Advisor
Commercial framework
A
C
R
C
C
TULIP / PECOS / CMS
A
R
C
C
C
Clinical policy + QAPI
A
R
C
R
C
Staffing + payroll build
A
R
R
R
C
EMR + billing readiness
A
R
R
R
C
Finance + reconciliation
A
R
R
C
C
First-admission readiness
A
R
R
R
C
A = accountable | R = responsible | C = consulted
Names replace placeholders after Patrick maps his team.
Notes: This is a discussion draft. Resolve role conflicts in the detailed appendix.
[Sources]
- Internal working assumptions confirmed by Geoff Schackmann, August 6, 2026.

## Slide 15
PROFOUND × AZALEA | TYLER ADS
The document package separates today’s framework from binding obligations
15
01
Term sheet + implementation letter
Non-binding business framework; any payment or implementation obligation expressly binding or placed in a short letter
02
Counsel memorandum
Structure, guardrails, open legal questions and definitive-document architecture
03
Financial-advisor memorandum
Funding, cash controls, payroll, reporting, reserves and open assumptions
04
Definitive agreement suite
Management, funding, reimbursement, employment, data, vendors, indemnity and transition
Patrick and Geoff align on the working drafts before distribution. Advisors redline within agreed response windows and preserve the agreed commercial intent.
Notes: [Sources]
- Profound Counsel Memorandum - Working Draft Revision 1.00 - 080626.
- Profound Financial Advisor Memorandum - Working Draft Revision 1.00 - 080626.
- Internal working assumptions confirmed by Geoff Schackmann, August 6–7, 2026.

## Slide 16
PROFOUND × AZALEA | TYLER ADS
Leave Monday with a signed framework, six decisions and named owners
16
1
Confirm the $7,500 fee, direct-cost rules, 12-month term and mutual extension
2
Set Patrick’s transition election—or a firm date to choose cash versus the note
3
Agree on the binding instrument for the September 1 implementation payment
4
Approve payroll, cash, EMR and DME recommendations for advisor validation
5
Name regulatory filing owners and Profound’s final go/no-go signer
6
Finalize and sign the non-binding framework before the meeting adjourns
Target
Walk out with a signed framework, decision log, owners and dates; launch only after written approval and readiness evidence.
Notes: [Sources]
- Profound Counsel Memorandum - Working Draft Revision 1.00 - 080626.
- Profound Financial Advisor Memorandum - Working Draft Revision 1.00 - 080626.
- Internal working assumptions confirmed by Geoff Schackmann, August 6–7, 2026.

## Slide 17
PROFOUND × AZALEA | TYLER ADS
Record the agreement before the meeting ends
17
1
Commercial terms | Agreed / Open: ______________________________
2
Transition option | Cash / Note / Decision date: ________________
3
Payment instrument | Binding provision / Short letter: __________
4
Payroll + cash controls | Approved / Open: ______________________
5
EMR + DME path | Owner and due date: __________________________
6
Launch authority | Owner, evidence and go/no-go signer: __________
Meeting close
Non-binding framework signed today; every open item recorded with one owner and one deadline.
Notes: [Sources]
- Profound Counsel Memorandum - Working Draft Revision 1.00 - 080626.
- Profound Financial Advisor Memorandum - Working Draft Revision 1.00 - 080626.
- Internal working assumptions confirmed by Geoff Schackmann, August 6–7, 2026.

## Slide 18
PROFOUND × AZALEA | TYLER ADS
Convert the signed framework into work during the first 10 business days
18
1
Patrick sends aligned memoranda to counsel and financial advisor | Owner/date: __________
2
Counsel confirms structure, payment instrument and enrollment path | Due: __________
3
Financial advisor confirms prefunding, reserves, payroll, reconciliation and FMV | Due: __________
4
Profound opens TULIP, PECOS/MAC and accreditation workstreams | Owner/date: __________
5
Teams complete EMR, DME, billing, payroll, insurance and staffing diligence | Due: __________
6
Joint team maintains the evidence tracker and weekly go/no-go review | Owner: __________
Launch discipline
No first admission until Profound signs the readiness certificate and every required approval is effective.
Notes: [Sources]
- Profound Counsel Memorandum - Working Draft Revision 1.00 - 080626.
- Profound Financial Advisor Memorandum - Working Draft Revision 1.00 - 080626.
- Internal working assumptions confirmed by Geoff Schackmann, August 6–7, 2026.

## Slide 19
PROFOUND × AZALEA | TYLER ADS
Set response dates so advisor review does not stall implementation
19
01
Counsel memorandum
Recipient: __________________ | Send: __________ | Redline due: __________
02
Financial-advisor memorandum
Recipient: __________________ | Send: __________ | Response due: __________
03
Term sheet + implementation letter
Owners: Geoff + Patrick | Counsel mark-up: __________ | Signature: __________
04
Definitive agreement suite
Counsel: __________ | Draft: __________ | Execution: __________
Open legal or financial issues go into one decision log; they do not silently change the agreed commercial intent.
Notes: [Sources]
- Profound Counsel Memorandum - Working Draft Revision 1.00 - 080626.
- Profound Financial Advisor Memorandum - Working Draft Revision 1.00 - 080626.
- Internal working assumptions confirmed by Geoff Schackmann, August 6–7, 2026.

## Slide 20
APPENDIX
Working materials
for implementation
Detailed launch checklist • Expanded RACI • Vendor diligence • Calendar
Notes: [Sources]
- Internal working assumptions confirmed by Geoff Schackmann, August 6, 2026.

## Slide 21
WORKING APPENDIX
Appendix A — Regulatory and operating launch checklist
21
Provider facts
License, service area, CCN/NPI, MAC, accreditation, current enrollment data
Texas
TULIP access, ADS application, location, leadership, policies and supporting documents
Medicare
PECOS/CMS-855A location addition, required disclosures, MAC/state/AO coordination
Clinical
Staffing, policies, QAPI, IDG, medical director, 24/7 coverage and competencies
Systems
EMR control, billing configuration, clearinghouse, DDE, records and cybersecurity
Vendors
DME, pharmacy, supplies, lab, facilities, insurance and service-level agreements
Finance
Banking, subledger, payroll, reserves, reconciliation and monthly close
Launch gate
Written approvals, testing, orientation, mock admission and signed readiness certificate
Notes: [Sources]
- Texas TULIP training guide: https://www.hhs.texas.gov/sites/default/files/documents/doing-business-with-hhs/licensing-credentialing-regulation/tulip/tulip-training-guide.pdf
- CMS-855A: https://www.cms.gov/medicare/cms-forms/cms-forms/downloads/cms855a.pdf
- 42 C.F.R. § 418.100(f): https://www.ecfr.gov/current/title-42/chapter-IV/subchapter-B/part-418/subpart-D/section-418.100

## Slide 22
WORKING APPENDIX
Appendix B — Detailed RACI
22
Workstream
Profound
Azalea
Tyler team
Advisor / vendor
Commercial + documents
A
R
C
C
TULIP + state license
A/R
C
C
C
PECOS / 855A + MAC
A/R
C
C
C
Clinical policies + QAPI
A
C
R
C
Staff employment + payroll
A
R
R
C
FireNote / EMR decision
A
R
R
C
DME + other vendors
A
R
R
C
Billing + cash + close
A
R
C
C
Training + mock admission
A
R
R
C
Replace role-level placeholders with names, due dates and evidence of completion during the meeting.
Notes: [Sources]
- Internal working assumptions confirmed by Geoff Schackmann, August 6, 2026.

## Slide 23
WORKING APPENDIX
Appendix C — Vendor approval gates
23
EMR
□ Profound administrator access
□ Complete authoritative record
□ Audit trail and authentication
□ Export and six-year retention
□ HIPAA / BAA / security review
□ HOPE, QAPI and supervisory workflows
□ Claims, ERA and AR configuration
□ Training and support plan
DME
□ Profound-approved agreement
□ Service-area coverage
□ 24/7 service and escalation
□ Formulary and authorization rules
□ Pricing and invoice detail
□ EMR integration
□ Patient transition protocol
□ Retrieval and equipment ownership
Payroll + billing
□ One quarterly tax filer
□ Profound employer setup
□ Tyler department / cost center
□ Azalea prefunding mechanics
□ Claims credentials and clearinghouse
□ DDE / eligibility access
□ Patient-level cash attribution
□ Monthly reconciliation calendar
Notes: [Sources]
- 42 C.F.R. § 418.104: https://www.law.cornell.edu/cfr/text/42/418.104
- CMS-855A: https://www.cms.gov/medicare/cms-forms/cms-forms/downloads/cms855a.pdf
- Gusto filing guidance: https://support.gusto.com/article/250327190420853/payroll-tax-responsibilities-when-switching-to-gusto

## Slide 24
WORKING APPENDIX
Appendix D — Implementation calendar
24
Aug 10
Aug 11–14
Aug 17–21
Aug 24–28
Aug 31
Sep 1
Framework + owners
Counsel / advisor review
TULIP + PECOS / CMS pathway
Payroll, EMR + vendor setup
Policies, training + testing
Readiness gate + first admission
$7,500 implementation payment
The sequence is directional until Profound’s licensing specialist, MAC, accreditation organization and counsel confirm the actual approval path.
Notes: [Sources]
- Texas TULIP training guide: https://www.hhs.texas.gov/sites/default/files/documents/doing-business-with-hhs/licensing-credentialing-regulation/tulip/tulip-training-guide.pdf
- CMS institutional enrollment guidance: https://www.cms.gov/medicare/enrollment-renewal/providers-suppliers/chain-ownership-system-pecos/enroll-as-institutional-provider