## Slide 1
WORKING SESSION
Profound × Azalea
Tyler ADS Partnership
August 10, 2026 | 1:00–5:00 p.m. CT | Austin area
Objective: document the framework, assign the launch work, and begin implementation.
Notes: Open collaboratively: the business concept is aligned; this meeting is about making the work executable.
[Sources]
- Internal working assumptions confirmed by Geoff Schackmann, August 6, 2026.

## Slide 2
PROFOUND × AZALEA | TYLER ADS
Today should convert alignment into an executable path
02
01
Confirm the operating and economic framework
02
Resolve authority, staffing, payroll, EMR and vendor decisions
03
Agree on TULIP, PECOS and Medicare approval workstreams
04
Assign accountable owners and target dates
05
Approve the advisor packages and document architecture
06
Finalize the non-binding term sheet for signature
Notes: Use this as the upfront contract for the four-hour working session.
[Sources]
- Internal working assumptions confirmed by Geoff Schackmann, August 6, 2026.

## Slide 3
PROFOUND × AZALEA | TYLER ADS
The concept is aligned; four items remain to be documented
03
Aligned in principle
• Tyler ADS under Profound’s provider platform
• Azalea funds the Tyler operation
• $7,500 monthly implementation and oversight fee
• Direct costs reimbursed at cost, without markup
Still to document
• Final authority and responsibility matrix
• Payroll, EMR, billing and vendor controls
• Advisor review and definitive-document path
• Regulatory sequence and launch conditions
Working status
Agreement in principle — subject to financial-advisor review, legal review, regulatory approval and definitive documents.
Notes: Do not describe the relationship as executed or approved yet.
[Sources]
- Internal working assumptions confirmed by Geoff Schackmann, August 6, 2026.

## Slide 4
PROFOUND × AZALEA | TYLER ADS
Profound receives near-term economics and a stronger operating partner
04
Immediate value
$7,500 monthly fee
Full reimbursement of direct Tyler costs
No Tyler capital obligation
Transition consideration selected by Patrick
Operating value
Experienced clinical and growth team
Tyler execution without distracting Profound’s current operation
Shared operating, documentation and marketing practices
Transparent performance reporting
Strategic option
A 12-month bridge with a mutual extension option
A working relationship that may continue after Azalea’s standalone platform
No automatic long-term equity or permanent dependency
Notes: Lead with value, then acknowledge that provider-level risk is why Profound retains control and protections.
[Sources]
- Internal working assumptions confirmed by Geoff Schackmann, August 6, 2026.

## Slide 5
PROFOUND × AZALEA | TYLER ADS
Profound retains provider authority while Tyler economics stay separate
05
Tyler Hold / Geoff
Funds Tyler
Provides management infrastructure
Tyler ADS
Separate cost center
Local team and operating plan
Profound Hospice
Licensed provider
Final clinical and compliance authority
Payers
Claims and
receipts
Profound must remain the actual provider—not a billing conduit.
Clinical authority, records, claims, cash, QAPI and stop-admission rights trace back to Profound. Azalea’s independence is created through funding, local management, reporting and transition rights.
Notes: Use ‘provider platform’ and ‘approved ADS,’ never ‘renting the license.’
[Sources]
- 42 C.F.R. § 418.100(b), (e)–(f): https://www.ecfr.gov/current/title-42/chapter-IV/subchapter-B/part-418/subpart-D/section-418.100
- Texas HHSC ADS guidance: https://apps.hhs.texas.gov/providers/hcssa/cbt/module6/HCSSA_PresurveyCBT_Module_6_0603202121.html

## Slide 6
PROFOUND × AZALEA | TYLER ADS
The economics are fixed, transparent and independent of referrals
06
Monthly
$7,500
First payment: September 1
Triggered by the signed non-binding framework and formal implementation—not access to credentials.
Direct costs
Reimbursed at actual cost
No markup
Documented and reconciled monthly
No Profound capital obligation
Patrick’s election
Option A
$25,000 cash after defined transition obligations
Option B
$50,000 convertible note; definitive terms developed with counsel
No exclusivity
Notes: Confirm that the September payment compensates implementation and oversight work.
[Sources]
- Internal working assumptions confirmed by Geoff Schackmann, August 6, 2026.

## Slide 7
PROFOUND × AZALEA | TYLER ADS
Profound’s protections are embedded in the operating model
07
01
Authority
Final admissions, clinical, policy, QAPI, billing and stop-admission control
02
Cash
Profound-controlled bank account and payer receipts
03
Visibility
Tyler claims, ERA, AR, payroll and vendor reporting
04
Funding
Azalea-prefunded payroll, operating costs and required reserves
05
Recourse
Insurance, indemnity, audit cooperation and wind-down obligations
Notes: Invite Patrick to identify any risk that is not already allocated.
[Sources]
- 42 C.F.R. § 418.100(b), (e)–(f): https://www.ecfr.gov/current/title-42/chapter-IV/subchapter-B/part-418/subpart-D/section-418.100
- Texas HHSC ADS guidance: https://apps.hhs.texas.gov/providers/hcssa/cbt/module6/HCSSA_PresurveyCBT_Module_6_0603202121.html

## Slide 8
PROFOUND × AZALEA | TYLER ADS
The teams integrate around clear decision rights
08
Tyler / Azalea leads
• Local execution and census development
• Recruiting and staffing recommendations
• Scheduling and performance management
• Marketing and referral-development activity
• Tyler budget and operating reporting
• Technology and vendor recommendations
Profound retains final authority
• Patient acceptance and discharge
• Eligibility, certification and plan of care
• Clinical policies and QAPI
• Provider enrollment, claims and refunds
• Final clinical employment decisions
• Stop-admission and compliance intervention
Integration action
Introduce both teams, explain the shared model, and publish one escalation path before the first admission.
Notes: Silas should lead this section and invite Patrick to map his existing team into the roles.
[Sources]
- Texas HHSC ADS guidance on authority and supervision: https://apps.hhs.texas.gov/providers/hcssa/cbt/module6/HCSSA_PresurveyCBT_Module_6_0603202121.html

## Slide 9
PROFOUND × AZALEA | TYLER ADS
Vendor choices should reduce risk—not create friction
09
FireNote
Azalea’s proposed Tyler EMR
Rationale: documentation consistency, clinician productivity and compliance visibility
Decision requires Profound control, administrator access, record export, claims workflow and security review
Hospice Tools
Profound’s current EMR
Known operating environment for Profound
Published pricing starts at $85 per user/month; billing and clearinghouse services may be separate
Evaluate integration and total workflow cost
DME Express
Azalea’s current DME partner
Continuity reduces patient and caregiver disruption
Profound must approve a new agreement or valid assignment
Confirm formulary, service levels, integration, pricing and invoicing
Notes: Do not present FireNote as predetermined. Present a controlled clinical review and shared decision.
[Sources]
- FireNote product claims (vendor-provided): https://firenote.health/compliance-solutions and https://firenote.health/how-firenote-works
- Hospice Tools pricing and product claims (vendor-provided): https://www.hospicetools.com/pricing/
- DME Express integration claims (vendor-provided): https://dmeexpress.com/technology/

## Slide 10
PROFOUND × AZALEA | TYLER ADS
A clinical working session can decide the EMR based on evidence
10
Participants
Patrick • Patrick’s RN spouse • Profound clinical lead • Dana • Silas • FireNote implementation lead
1
Demonstrate
Admission, care plan, IDG, orders, HOPE, supervisory visits and ADR retrieval
2
Validate control
Profound administrator access, audit logs, policy alignment, record retention and export
3
Validate billing
NPI/CCN configuration, NOE and claim workflow, clearinghouse, ERA and AR reporting
4
Decide
Approve FireNote, retain Hospice Tools, or define a controlled alternative
Notes: Offer to schedule this follow-up immediately. The clinical users should decide against agreed acceptance criteria.
[Sources]
- 42 C.F.R. § 418.104: https://www.law.cornell.edu/cfr/text/42/418.104
- CMS-855A medical-record storage and provider-control instructions: https://www.cms.gov/medicare/cms-forms/cms-forms/downloads/cms855a.pdf

## Slide 11
PROFOUND × AZALEA | TYLER ADS
Core clinical staff should sit on Profound payroll; Azalea funds the cost
11
Recommended base case
• Profound is W-2 employer for core clinical staff
• Azalea prefunds wages, taxes and benefits
• Tyler is a separate location and cost center
• One authoritative payroll-tax filer
• Gusto only if Profound’s payroll advisor validates the configuration
• Azalea employs appropriate nonclinical staff
Why this is cleaner
• Aligns employment with the certified provider
• Preserves Profound’s supervision and policy authority
• Avoids routine contracting of core services
• Prevents duplicate quarterly payroll filings
• Produces location-level payroll reporting
• Keeps Azalea economically responsible
Decision needed
Authorize payroll and healthcare counsel to validate the employer, funding and filing mechanics immediately.
Notes: Do not promise that two unrelated payroll providers can file under one EIN. The base case requires one filer.
[Sources]
- 42 C.F.R. § 418.64 core-services employment rule: https://ecfr.io/Title-42/Section-418.64
- 42 C.F.R. § 418.100 governing-body and administrator requirements: https://www.ecfr.gov/current/title-42/chapter-IV/subchapter-B/part-418/subpart-D/section-418.100
- Gusto guidance on one filer per quarter: https://support.gusto.com/article/250327190420853/payroll-tax-responsibilities-when-switching-to-gusto

## Slide 12
PROFOUND × AZALEA | TYLER ADS
One bank account and one Tyler subledger keep cash controls clean
12
Payers
Deposit into Profound-controlled account
Tyler subledger
Patient, claim, ERA, AR and cash attribution
Payment waterfall
Care costs → reimbursements → fee → reserves → true-up
Report
Monthly close and variance review
Minimum monthly reporting
• Claims submitted, paid, denied and pending
• ERA and cash receipts by patient and service month
• Payroll, pharmacy, DME and other direct costs
• Fee, reserve activity and working-capital balance
• Reconciliation, exceptions and agreed true-up
Control principle
Profound controls payer cash. Azalea receives complete visibility and contractual reconciliation rights.
Notes: Use this slide to agree on the close calendar and access—not just the abstract waterfall.
[Sources]
- CMS-855A payment and record-control instructions: https://www.cms.gov/medicare/cms-forms/cms-forms/downloads/cms855a.pdf
- Internal working assumptions confirmed by Geoff Schackmann, August 6, 2026.

## Slide 13
PROFOUND × AZALEA | TYLER ADS
Billing readiness is a regulatory project—not a credential handoff
13
1
Confirm eligibility
Service area, location, license status, accreditation and MAC pathway
2
Texas TULIP
Submit the ADS application and required supporting information
3
PECOS / 855A
Add the hospice treatment location and disclose required control information
4
Approval + build
CMS/MAC/state/AO review; policies, staffing, EMR, vendors and readiness
5
First admission
Only after required approvals are effective and launch controls pass
August 31 is an aggressive target. The parties should launch only after approval—not back into approval from a promised date.
Notes: Ask Patrick to identify his MAC, accreditation organization, current licensed service area and TULIP access during the meeting.
[Sources]
- Texas TULIP training guide: https://www.hhs.texas.gov/sites/default/files/documents/doing-business-with-hhs/licensing-credentialing-regulation/tulip/tulip-training-guide.pdf
- Texas HHSC ADS guidance: https://apps.hhs.texas.gov/providers/hcssa/cbt/module6/HCSSA_PresurveyCBT_Module_6_0603202121.html
- 42 C.F.R. § 418.100(f): https://www.ecfr.gov/current/title-42/chapter-IV/subchapter-B/part-418/subpart-D/section-418.100
- CMS-855A, Section 4: https://www.cms.gov/medicare/cms-forms/cms-forms/downloads/cms855a.pdf

## Slide 14
PROFOUND × AZALEA | TYLER ADS
The RACI keeps Profound accountable without making Patrick do everything
14
Workstream
Patrick
Profound role
Geoff
Silas
Advisor
Commercial framework
A
C
R
C
C
TULIP / PECOS / CMS
A
R
C
C
C
Clinical policy + QAPI
A
R
C
R
C
Staffing + payroll build
A
R
R
R
C
EMR + billing readiness
A
R
R
R
C
Finance + reconciliation
A
R
R
C
C
First-admission readiness
A
R
R
R
C
A = accountable | R = responsible | C = consulted
Names replace placeholders after Patrick maps his team.
Notes: This is a discussion draft. Resolve role conflicts in the detailed appendix.
[Sources]
- Internal working assumptions confirmed by Geoff Schackmann, August 6, 2026.

## Slide 15
PROFOUND × AZALEA | TYLER ADS
Four documents move the framework from discussion to implementation
15
01
Non-binding term sheet
Business terms, implementation trigger, advisor process and next steps
02
Counsel memorandum
Structure, guardrails, open legal questions and definitive-document architecture
03
Financial-advisor memorandum
Funding, cash controls, payroll, reporting, reserves and open assumptions
04
Definitive agreements
Management, funding, reimbursement, employment, data, vendors, indemnity and transition
Patrick redlines the advisor memoranda before distributing them. Counsel and the financial advisor validate—not redesign—the agreed commercial intent.
Notes: Confirm who owns each document, the first-review date and the decision deadline.
[Sources]
- Internal working assumptions confirmed by Geoff Schackmann, August 6, 2026.

## Slide 16
PROFOUND × AZALEA | TYLER ADS
Leave Monday with six decisions and named owners
16
1
Confirm the commercial terms and September 1 implementation payment
2
Approve the recommended payroll and cash-control design for advisor validation
3
Authorize the FireNote / Hospice Tools clinical review and DME contracting work
4
Confirm the regulatory critical path and responsible filing parties
5
Approve the counsel and financial-advisor packages for Patrick’s redline
6
Finalize and sign the non-binding term sheet shortly after the meeting
Target
Readiness to admit by August 31—only if all required approvals and controls are complete.
Notes: Close by reading each decision aloud and assigning one accountable owner and date.
[Sources]
- Internal working assumptions confirmed by Geoff Schackmann, August 6, 2026.

## Slide 17
APPENDIX
Working materials
for implementation
Detailed launch checklist • Expanded RACI • Vendor diligence • Calendar
Notes: [Sources]
- Internal working assumptions confirmed by Geoff Schackmann, August 6, 2026.

## Slide 18
WORKING APPENDIX
Appendix A — Regulatory and operating launch checklist
18
Provider facts
License, service area, CCN/NPI, MAC, accreditation, current enrollment data
Texas
TULIP access, ADS application, location, leadership, policies and supporting documents
Medicare
PECOS/CMS-855A location addition, required disclosures, MAC/state/AO coordination
Clinical
Staffing, policies, QAPI, IDG, medical director, 24/7 coverage and competencies
Systems
EMR control, billing configuration, clearinghouse, DDE, records and cybersecurity
Vendors
DME, pharmacy, supplies, lab, facilities, insurance and service-level agreements
Finance
Banking, subledger, payroll, reserves, reconciliation and monthly close
Launch gate
Written approvals, testing, orientation, mock admission and signed readiness certificate
Notes: [Sources]
- Texas TULIP training guide: https://www.hhs.texas.gov/sites/default/files/documents/doing-business-with-hhs/licensing-credentialing-regulation/tulip/tulip-training-guide.pdf
- CMS-855A: https://www.cms.gov/medicare/cms-forms/cms-forms/downloads/cms855a.pdf
- 42 C.F.R. § 418.100(f): https://www.ecfr.gov/current/title-42/chapter-IV/subchapter-B/part-418/subpart-D/section-418.100

## Slide 19
WORKING APPENDIX
Appendix B — Detailed RACI
19
Workstream
Profound
Azalea
Tyler team
Advisor / vendor
Commercial + documents
A
R
C
C
TULIP + state license
A/R
C
C
C
PECOS / 855A + MAC
A/R
C
C
C
Clinical policies + QAPI
A
C
R
C
Staff employment + payroll
A
R
R
C
FireNote / EMR decision
A
R
R
C
DME + other vendors
A
R
R
C
Billing + cash + close
A
R
C
C
Training + mock admission
A
R
R
C
Replace role-level placeholders with names, due dates and evidence of completion during the meeting.
Notes: [Sources]
- Internal working assumptions confirmed by Geoff Schackmann, August 6, 2026.

## Slide 20
WORKING APPENDIX
Appendix C — Vendor approval gates
20
EMR
□ Profound administrator access
□ Complete authoritative record
□ Audit trail and authentication
□ Export and six-year retention
□ HIPAA / BAA / security review
□ HOPE, QAPI and supervisory workflows
□ Claims, ERA and AR configuration
□ Training and support plan
DME
□ Profound-approved agreement
□ Service-area coverage
□ 24/7 service and escalation
□ Formulary and authorization rules
□ Pricing and invoice detail
□ EMR integration
□ Patient transition protocol
□ Retrieval and equipment ownership
Payroll + billing
□ One quarterly tax filer
□ Profound employer setup
□ Tyler department / cost center
□ Azalea prefunding mechanics
□ Claims credentials and clearinghouse
□ DDE / eligibility access
□ Patient-level cash attribution
□ Monthly reconciliation calendar
Notes: [Sources]
- 42 C.F.R. § 418.104: https://www.law.cornell.edu/cfr/text/42/418.104
- CMS-855A: https://www.cms.gov/medicare/cms-forms/cms-forms/downloads/cms855a.pdf
- Gusto filing guidance: https://support.gusto.com/article/250327190420853/payroll-tax-responsibilities-when-switching-to-gusto

## Slide 21
WORKING APPENDIX
Appendix D — Implementation calendar
21
Aug 10
Aug 11–14
Aug 17–21
Aug 24–28
Aug 31
Sep 1
Framework + owners
Counsel / advisor review
TULIP + PECOS / CMS pathway
Payroll, EMR + vendor setup
Policies, training + testing
Readiness gate + first admission
$7,500 implementation payment
The sequence is directional until Profound’s licensing specialist, MAC, accreditation organization and counsel confirm the actual approval path.
Notes: [Sources]
- Texas TULIP training guide: https://www.hhs.texas.gov/sites/default/files/documents/doing-business-with-hhs/licensing-credentialing-regulation/tulip/tulip-training-guide.pdf
- CMS institutional enrollment guidance: https://www.cms.gov/medicare/enrollment-renewal/providers-suppliers/chain-ownership-system-pecos/enroll-as-institutional-provider